## README
TestMarkaz — Planning Workbook
Document version | 1.0
Date | May 2026
Target market | Uzbekistan (primary)
Team context | Solo founder / very small team
Contents
Sheet | Description
Feature Matrix | Subscription tiers × features (Free / Premium / Tutor Pro / Center)
DB Schema | Tables, key columns, indexes, row size, year-1 estimate
API Endpoints | Full REST surface; method, path, auth, rate limit
MVP Roadmap | Week-by-week plan for Phase 0 → Phase 2 (32 weeks)
Cost Model | Monthly infra + AI + people costs, with formulas
Revenue Model | MAU → conversion → MRR projection year 1
AI Cost Calculator | Token-based cost per user per day; tweak to see margin
Risk Register | Risks, likelihood, impact, mitigations
KPI Dashboard | Targets and progress at MVP / Year 1 milestones

## Feature Matrix
Subscription Feature Matrix
Feature | Free | Premium | Tutor Pro | Center
Price (UZS / month) | 0 | 29,000 | 99,000 | 990,000 + 9,000/student
Price (USD) | 0 | $2.30 | $7.90 | $78 + $0.71/student
Read curated books | ✓ | ✓ | ✓ | ✓
Practice questions / day | 20 | Unlimited | Unlimited | Unlimited
Timed mock exams | 1/week | Unlimited | Unlimited | Unlimited
AI question generation / month | — | 100 | 500 | 2,000
AI study assistant messages / day | 10 | 100 | 200 | 300/student
Detailed analytics | Last 7 days | Full history | Full + per-class | Full
Weak-topic recommendations | — | ✓ | ✓ | ✓
Offline reading (books) | 1 | 10 | Unlimited | Unlimited
Ads | Yes | No | No | No
Streak freezes / month | 1 | 5 | 10 | 10/student
Voice mode (Whisper + TTS) | — | ✓ | ✓ | ✓
Upload own books | — | 3 | 50 | Unlimited
Classroom tools | — | — | 3 classrooms | Unlimited
Bulk student onboarding | — | — | — | ✓
White-label landing | — | — | — | ✓
AI credit packs (top-up) | ✓ | ✓ | ✓ | ✓

## DB Schema
PostgreSQL Schema — Tables Overview
Module | Table | Purpose | Key columns | Indexes | Avg row size | Yr-1 rows | Yr-1 storage
auth | users | Identity, role, locale, premium flags | id, public_id, email/phone, role, grade, region, is_premium | (role,grade); (region) | 1 KB | 250000 | 250 MB
auth | social_accounts | Google/Apple/Telegram links | user_id, provider, provider_uid | (provider,provider_uid) | 0.3 KB | 80000 | 24 MB
auth | user_devices | FCM token, last seen, platform | user_id, device_uid, platform, push_token | (user_id,device_uid) unique | 0.3 KB | 400000 | 120 MB
auth | sessions | Hashed refresh tokens | user_id, refresh_token_hash, expires_at | (user_id) where active | 0.4 KB | 600000 | 240 MB
taxonomy | subjects | Localised subject catalogue | code, name_uz/ru/en | — | 0.5 KB | 30 | <1 MB
taxonomy | exam_types | DTM, IELTS, school_final, ... | code, country | — | 0.4 KB | 20 | <1 MB
taxonomy | topics | Hierarchical topic tree | subject_id, parent_id, code, grade | (subject_id,grade) | 0.5 KB | 2500 | 1 MB
books | books | Metadata + R2 key | subject_id, grade, language, file_url, status | (subject,grade,lang); (status) | 1.5 KB | 5000 | 8 MB
books | chapters | Per-book chapter list | book_id, number, start_page, end_page, topic_id | (book_id) | 0.5 KB | 75000 | 38 MB
books | pages | Page text + tsvector | book_id, page_number, text, text_tsv | GIN(text_tsv); (book,chapter) | 5 KB | 5000000 | 25 GB
books | book_chunks | RAG payload; vector in Qdrant | book_id, chapter_id, text, qdrant_point_id, content_hash | (book,chapter); (hash) | 2 KB | 25000000 | 50 GB
books | bookmarks | Per-user page bookmarks | user_id, book_id, page | (user,book,page) unique | 0.2 KB | 1000000 | 200 MB
books | highlights | Per-user highlights | user_id, book_id, selection, position | (user,book) | 0.5 KB | 500000 | 250 MB
books | user_book_progress | Last page, time spent | user_id, book_id, last_page, read_seconds | PK(user,book) | 0.2 KB | 800000 | 160 MB
ai | questions | AI-generated or curated | book_id, chapter_id, type, difficulty, language, prompt | (book,chapter); (topic,difficulty) | 1 KB | 15000000 | 15 GB
ai | question_options | MCQ options | question_id, letter, text, is_correct | PK(question,letter) | 0.3 KB | 50000000 | 15 GB
ai | flashcards | SM-2 state per user | user_id, ease, interval_days, due_at | (user,due_at) | 0.5 KB | 5000000 | 2.5 GB
ai | ai_jobs | Background job ledger w/ cost | type, payload, status, cost_cents | (status,type) | 1 KB | 2000000 | 2 GB
ai | ai_chat_threads | Assistant threads | user_id, book_id, title | (user_id) | 0.5 KB | 200000 | 100 MB
ai | ai_chat_messages | Chat history with citations | thread_id, role, content, citations | (thread,created_at) | 1 KB | 50000000 | 50 GB
exams | exams | Exam definitions | subject_id, exam_type_id, duration_sec, randomize | — | 1 KB | 5000 | 5 MB
exams | exam_questions | Junction table | exam_id, question_id, position, points | PK(exam,question) | 0.2 KB | 250000 | 50 MB
exams | attempts | Per-user attempt; server ends_at | user_id, exam_id, question_set[], ends_at | (user,started_at) | 0.3 KB | 30000000 | 9 GB
exams | answers | Each question response | attempt_id, question_id, selected_option, is_correct | PARTITION BY MONTH | 0.2 KB | 600000000 | 120 GB
analytics | study_sessions | Session start/end | user_id, started_at, ended_at | (user,started_at) | 0.2 KB | 30000000 | 6 GB
analytics | topic_mastery | Elo-style mastery | user_id, topic_id, mastery, accuracy | PK(user,topic); (user,mastery) | 0.3 KB | 25000000 | 7.5 GB
gamification | streaks | Per-user streak | user_id, current_days, longest_days | PK(user) | 0.1 KB | 250000 | 25 MB
gamification | xp_events | XP awards ledger | user_id, reason, amount | (user,created_at) | 0.2 KB | 100000000 | 20 GB
gamification | badges | Catalogue | code, name_uz/ru/en, criteria | — | 0.5 KB | 50 | <1 MB
gamification | user_badges | Earned badges | user_id, badge_id, awarded_at | PK(user,badge) | 0.1 KB | 2000000 | 200 MB
gamification | leaderboard_snapshots | Daily materialised | snapshot_date, scope, rank, xp | PK(date,scope,user) | 0.2 KB | 30000000 | 6 GB
classrooms | classrooms | Teacher-owned class | name, join_code, teacher_id, subject_id | (join_code) unique | 0.5 KB | 5000 | 2.5 MB
classrooms | classroom_memberships | Student↔class | classroom_id, user_id, role | PK(class,user) | 0.1 KB | 150000 | 15 MB
classrooms | assignments | Homework | classroom_id, exam_id, book_id, due_at | (classroom_id) | 0.5 KB | 50000 | 25 MB
billing | subscription_plans | Plans catalogue | code, price_cents, currency, interval | — | 0.5 KB | 10 | <1 MB
billing | subscriptions | User sub state machine | user_id, plan_id, status, current_period_end | (user) where active | 0.5 KB | 30000 | 15 MB
billing | payments | Provider receipts | provider, provider_ref, amount, raw JSONB | (provider,ref); (user,created_at) | 1 KB | 200000 | 200 MB
billing | ai_credits_ledger | Append-only credit history | user_id, delta, balance_after | (user,created_at) | 0.2 KB | 10000000 | 2 GB
admin | reports | Abuse/quality complaints | target_type, target_id, status, reason | (status) | 0.5 KB | 50000 | 25 MB
admin | audit_log | Every admin action | actor_id, action, target, metadata | (target_type,target_id) | 0.5 KB | 500000 | 250 MB
notifications | notifications | Per-user inbox | user_id, type, title, body, channel | (user) where unread | 0.5 KB | 50000000 | 25 GB

## API Endpoints
REST API Surface — /api/v1/...
Area | Method | Path | Auth | Rate limit (premium) | Description
Auth | POST | /auth/register | public | 5/min/IP | Email or phone + password
Auth | POST | /auth/login | public | 5/min/IP | Returns access + refresh tokens
Auth | POST | /auth/refresh | cookie/refresh | 30/min | Rotate access token
Auth | POST | /auth/logout | user | 60/min | Revoke refresh token
Auth | POST | /auth/social/google | public | 5/min/IP | Exchange Google ID token
Auth | POST | /auth/social/apple | public | 5/min/IP | Apple Sign-In
Auth | POST | /auth/social/telegram | public | 5/min/IP | Telegram Login Widget
Auth | POST | /auth/otp/request | public | 3/min/IP | Send Eskiz.uz SMS OTP
Auth | POST | /auth/otp/verify | public | 5/min/IP | Verify OTP + log in
Users | GET | /me | user | 1000/min | Current profile + flags
Users | PATCH | /me | user | 300/min | Update name, avatar, region, locale
Users | DELETE | /me | user | 5/day | GDPR soft-delete
Users | POST | /me/avatar | user | 60/min | Multipart upload
Users | GET | /me/devices | user | 60/min | List active devices
Users | DELETE | /me/devices/{id} | user | 60/min | Sign out device
Users | GET | /me/export | user | 1/day | GDPR async export
Taxonomy | GET | /subjects | public | 1000/min | Localized subject catalogue
Taxonomy | GET | /exam-types | public | 1000/min | DTM, school_final, IELTS, ...
Taxonomy | GET | /topics | public | 1000/min | Topic tree filtered by subject/grade
Books | GET | /books | user | 1000/min | Filter subject/grade/lang/exam/diff/q
Books | GET | /books/{id} | user | 1000/min | Detail + chapters
Books | GET | /books/{id}/chapters | user | 1000/min | Chapter list
Books | GET | /books/{id}/pages/{p} | user | 1000/min | Page text
Books | GET | /books/{id}/file | user | 60/min | Signed 5-min download URL
Books | POST | /books | teacher/admin | 60/min | Upload
Books | PATCH | /books/{id} | owner/admin | 60/min | Edit metadata
Books | DELETE | /books/{id} | owner/admin | 60/min | Soft delete
Books | POST | /books/{id}/process | admin | 30/min | Reprocess (admin)
Books | GET | /books/{id}/search | user | 120/min | Full-text + semantic
Books | GET/POST/DELETE | /bookmarks | user | 300/min | Bookmark CRUD
Books | GET/POST/DELETE | /highlights | user | 300/min | Highlight CRUD
Books | GET | /me/library | user | 300/min | Books with progress
Books | PUT | /me/library/{id}/progress | user | 300/min | Update last_page
AI | POST | /ai/jobs/generate-questions | user | 10/min | Async; SSE progress
AI | POST | /ai/jobs/summarize-chapter | user | 10/min | Async
AI | POST | /ai/jobs/generate-flashcards | user | 10/min | Async
AI | GET | /ai/jobs/{id} | user | 300/min | Status
AI | GET | /ai/jobs/{id}/stream | user | — | SSE: progress, question, done
AI | POST | /ai/jobs/{id}/cancel | user | 60/min | Cancel
AI | GET/POST | /ai/chats | user | 60/min | Threads
AI | GET | /ai/chats/{id}/messages | user | 300/min | History
AI | POST | /ai/chats/{id}/messages | user | 30/min | RAG chat via SSE
AI | DELETE | /ai/chats/{id} | user | 60/min | Delete
AI | GET | /me/ai-credits | user | 60/min | Balance + daily usage
AI | POST | /me/ai-credits/purchase | user | 30/min | Click/Payme checkout
Exams | GET | /exams | user | 300/min | Filter subject/exam/diff
Exams | GET | /exams/{id} | user | 300/min | Detail (no Qs)
Exams | POST | /exams | teacher | 60/min | Create
Exams | PATCH | /exams/{id} | owner | 60/min | Edit
Exams | DELETE | /exams/{id} | owner | 60/min | Delete
Exams | POST | /exams/{id}/start | user | 30/min | Begin attempt
Exams | POST | /attempts/{id}/answer | user | 120/min | Submit answer
Exams | POST | /attempts/{id}/submit | user | 30/min | Finalize
Exams | GET | /attempts/{id} | user | 300/min | Results + explanations
Exams | GET | /me/attempts | user | 300/min | History
Practice | POST | /practice/start | user | 30/min | Random by subject/topic
Practice | POST | /practice/daily-challenge | user | 5/day | Today's challenge
Flashcards | GET | /me/flashcards/due | user | 300/min | Cards due now
Flashcards | POST | /me/flashcards/{id}/review | user | 300/min | SM-2 update
Flashcards | POST | /me/flashcards | user | 60/min | Create custom
Analytics | GET | /me/stats/overview | user | 300/min | XP, streak, accuracy
Analytics | GET | /me/stats/subjects | user | 300/min | Per-subject mastery
Analytics | GET | /me/stats/weak-topics | user | 300/min | Sorted by mastery
Analytics | GET | /me/stats/heatmap | user | 300/min | Daily heatmap
Analytics | GET | /me/recommendations | user | 60/min | AI-suggested next 5
Gamification | GET | /leaderboards | user | 300/min | Top 100 by scope
Gamification | GET | /me/badges | user | 300/min | Earned badges
Gamification | GET | /badges | user | 1000/min | Catalogue
Classrooms | GET | /classrooms | teacher | 300/min | List
Classrooms | POST | /classrooms | teacher | 60/min | Create
Classrooms | GET | /classrooms/{id} | member | 300/min | Detail + members
Classrooms | POST | /classrooms/{id}/join | user | 30/min | Join via code
Classrooms | DELETE | /classrooms/{id}/members/{u} | teacher | 60/min | Remove
Classrooms | GET/POST | /classrooms/{id}/assignments | teacher | 300/min | Assignments
Classrooms | GET | /classrooms/{id}/analytics | teacher | 300/min | Aggregate scores
Classrooms | GET | /classrooms/{id}/export | teacher | 30/min | CSV/XLSX export
Billing | GET | /billing/plans | public | 1000/min | Catalogue
Billing | GET | /me/subscription | user | 300/min | Active sub
Billing | POST | /billing/checkout | user | 30/min | Returns provider URL
Billing | POST | /billing/webhooks/click | public+sig | unlimited | Click webhook
Billing | POST | /billing/webhooks/payme | public+sig | unlimited | Payme webhook
Billing | POST | /billing/webhooks/stripe | public+sig | unlimited | Stripe webhook
Billing | POST | /me/subscription/cancel | user | 30/min | Cancel at period end
Billing | GET | /me/invoices | user | 300/min | Past invoices
Admin | GET | /admin/users | admin | 300/min | Search w/ filters
Admin | PATCH | /admin/users/{id} | admin | 300/min | Ban/role change
Admin | GET | /admin/books | admin | 300/min | Moderation queue
Admin | POST | /admin/books/{id}/approve | admin | 300/min | Approve
Admin | POST | /admin/books/{id}/reject | admin | 300/min | Reject w/ reason
Admin | GET | /admin/reports | admin | 300/min | Abuse reports
Admin | POST | /admin/reports/{id}/resolve | admin | 300/min | Resolve
Admin | GET | /admin/metrics | admin | 300/min | DAU, MAU, MRR, AI cost/day
Admin | GET | /admin/ai-cost | admin | 300/min | Per-user cost breakdown
Admin | POST | /admin/ai-cost/cap | admin | 60/min | Set per-user cap
Notifications | GET | /me/notifications | user | 300/min | Inbox
Notifications | PATCH | /me/notifications/{id} | user | 300/min | Mark read
Notifications | POST | /me/notifications/read-all | user | 300/min | Mark all
Notifications | POST | /me/push-token | user | 60/min | Register FCM
System | GET | /health | public | unlimited | Liveness
System | GET | /ready | public | unlimited | Readiness
System | GET | /version | public | unlimited | Build metadata

## MVP Roadmap
MVP Roadmap — Weeks 1 to 32
Phase | Weeks | Theme | Deliverables | Exit criteria / milestone
Phase 0 | 1-2 | Foundation | VPS provisioned; Supabase project; 4 repos + contracts repo; Ktor/Next/Flutter skeletons; CI/CD; Caddy+HTTPS; Sentry+UptimeRobot | User can register & log in on web + mobile; page loads <1s
Phase 1 | 3-4 | Book pipeline | Upload → R2; Tesseract OCR (uz/ru/en); chapter extractor; chunker+embedder→Qdrant; web reader (PDF.js); bookmarks/highlights; in-book search (Meilisearch) | Upload a 500-page textbook → chapters auto-detected in <5 min; search works
Phase 1 | 5-7 | AI question generator | generate-questions endpoint with SSE; gpt-4o-mini prompts in 3 languages; JSON-schema validation+dedup; question review UI; cost ledger + per-user budget | 20 MCQ + explanations from any chapter in <30s for ~$0.005
Phase 1 | 8-9 | Exam engine | Practice mode; timed exam (server-authoritative); auto-grading + explanations; daily challenge cron; streaks + XP | Student takes 30-min mock exam; sees 18/30 + per-question explanation
Phase 1 | 10-11 | Analytics | Topic mastery (Elo-like); weak-topic dashboard; recommendations; subject progress charts | Dashboard shows top-3 weak topics + next 5 actions
Phase 1 | 12-14 | Mobile (Flutter) | Auth, library, reader (flutter_pdfview), practice, exam (online); FCM push; payment deep links (stub) | Android in Play Store; 50 curated books seeded; founder daily user
Phase 2 | 15-18 | Payments (UZ) | Click full flow + webhooks; Payme; Atmos; Stripe (intl); subscription state machine + grace period | First paying user via Click; webhook idempotency tested
Phase 2 | 19-22 | Teacher panel | Classrooms + join codes; assignments; classroom analytics; CSV/XLSX export | 5 teachers from one Tashkent school running classrooms
Phase 2 | 23-26 | AI study assistant | Chat UI; SSE streaming; RAG scoped to user library + curated; mandatory citations; voice input (Whisper); TTS for premium | Student asks question in Uzbek → answer cites book page in <3s
Phase 2 | 27-28 | iOS launch | Apple Sign-In; TestFlight beta; App Store submission | iOS app live in App Store
Phase 2 | 29-30 | Flashcards + SRS | SM-2 algorithm; auto-gen from chapters; daily review widget | Daily flashcard widget in production
Phase 2 | 31-32 | Gamification polish | 50+ badges; region/grade/classroom leaderboards; streak freezes (premium) | 10k registered, 200 paying, $3k MRR

## Cost Model
Monthly Cost Model — Phase 1 to Year-1 Steady State
Category | Item | Phase 1 (USD) | Year-1 steady state (USD)
Infra | Hetzner CX32 VPS (Phase 1) / AX42 dedicated (Yr-1) | 6 | 80
Infra | Supabase (managed Postgres + Auth) | 25 | 150
Infra | Upstash Redis | 5 | 30
Infra | Cloudflare R2 (storage) | 7 | 40
Infra | Cloudflare Pages / Images / Stream | 0 | 20
Infra | Meilisearch hosted (Yr-1) | 0 | 50
Infra | Qdrant (self-hosted in Docker) | 0 | 0
AI | OpenAI API (chat + generation + embeddings) | 300 | 2800
AI | Google Vision OCR (fallback) | 10 | 80
Comms | Eskiz.uz SMS (~1k → ~10k OTPs) | 15 | 120
Comms | Postmark email | 0 | 25
Observability | Sentry / Grafana / Loki (paid tier Yr-1) | 0 | 80
Payments | Gateway fees (~2.5% of MRR) | 0 | 400
Marketing | Telegram ads + influencer + paid acquisition | 100 | 2000
People | Founder salary (modest) | 0 | 1500
People | Content lead (Yr-1 hire) | 0 | 1000
People | Design (project-based) | 100 | 300
Other | Domain + email + LLC | 5 | 30
TOTAL | — | 573 | 8705
| Annualized Phase 1 | 6876
| Annualized Year 1 steady | 104460

## Revenue Model
Revenue Projection — Month 1 to Month 12
Assumptions (BLUE = inputs)
Starting MAU (Month 1) | 200
Monthly growth rate | 45%
Free → Premium conversion % | 4%
Premium monthly UZS price | 29000
Premium yearly UZS price | 199000
Premium yearly cohort share | 20%
Tutor Pro subscribers (Month 12) | 50
Tutor Pro UZS price | 99000
Centers (Month 12) | 20
Avg students per center | 100
Center base UZS price | 990000
Center per-student UZS price | 9000
AI credit top-up takers (% of MAU) | 5%
Avg AI credit spend per user (UZS) | 30000
Mock exam buyers / month (Month 12) | 500
Mock exam price (UZS) | 50000
Free user ad RPM (USD) | 30%
Sessions per free user per month | 10
USD/UZS rate | 12500
Monthly Projection
Metric | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
MAU | 200 | 290 | 420.5 | 609.725 | 884.1013 | 1281.9468 | 1858.8229 | 2695.2932 | 3908.1751 | 5666.8539 | 8216.9382 | 11914.5603
Total Premium subs | 8 | 11.6 | 16.82 | 24.389 | 35.364 | 51.2779 | 74.3529 | 107.8117 | 156.327 | 226.6742 | 328.6775 | 476.5824
of which monthly | 6.4 | 9.28 | 13.456 | 19.5112 | 28.2912 | 41.0223 | 59.4823 | 86.2494 | 125.0616 | 181.3393 | 262.942 | 381.2659
of which yearly | 1.6 | 2.32 | 3.364 | 4.8778 | 7.0728 | 10.2556 | 14.8706 | 21.5623 | 31.2654 | 45.3348 | 65.7355 | 95.3165
Revenue (USD)
Premium monthly | 3.712 | 5.3824 | 7.8045 | 11.3165 | 16.4089 | 23.7929 | 34.4998 | 50.0246 | 72.5357 | 105.1768 | 152.5064 | 221.1342
Premium yearly (amortised) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tutor Pro (linear ramp) | 33 | 66 | 99 | 132 | 165 | 198 | 231 | 264 | 297 | 330 | 363 | 396
Centers (linear ramp) | 252 | 504 | 756 | 1008 | 1260 | 1512 | 1764 | 2016 | 2268 | 2520 | 2772 | 3024
AI credit top-ups | 24 | 34.8 | 50.46 | 73.167 | 106.0922 | 153.8336 | 223.0587 | 323.4352 | 468.981 | 680.0225 | 986.0326 | 1429.7472
Mock exams (ramp) | 166.6667 | 333.3333 | 500 | 666.6667 | 833.3333 | 1000 | 1166.6667 | 1333.3333 | 1500 | 1666.6667 | 1833.3333 | 2000
Ads (free tier) | 0.576 | 0.8352 | 1.211 | 1.756 | 2.5462 | 3.692 | 5.3534 | 7.7624 | 11.2555 | 16.3205 | 23.6648 | 34.3139
Total MRR (USD) | 476.2427 | 938.9685 | 1406.671 | 1881.5897 | 2366.9717 | 2867.5256 | 3390.0788 | 3944.531 | 4545.2366 | 5213.0097 | 5978.0307 | 6884.0612

## AI Cost Calculator
AI Cost Calculator — Per User Per Day
Inputs (BLUE)
gpt-4o-mini input $/M tokens | 0.15
gpt-4o-mini output $/M tokens | 0.6
text-embedding-3-small $/M tokens | 0.02
Avg chat messages / day (premium) | 30
Avg tokens per chat message in | 800
Avg tokens per chat message out | 300
Avg questions generated / day (premium) | 5
Avg tokens per generation in | 3000
Avg tokens per generation out | 1500
Avg embedding tokens / new book (per user share) | 100000
Books per user per month | 0.2
Cost calculation
Chat input cost / day | 0.0036
Chat output cost / day | 0.0054
Generation input cost / day | 0.00225
Generation output cost / day | 0.0045
Embedding cost / day (amortised) | 1.3333e-05
TOTAL cost / premium user / day | 0.015763
TOTAL / premium user / month | 0.4729
Premium price (USD) | 2.3
AI gross margin per user | 79.44%

## Risk Register
Risk Register
# | Risk | Category | Likelihood (1-5) | Impact (1-5) | Mitigation | Score
1 | AI costs spiral | Tech | 4 | 5 | Per-user daily cap, prompt caching, embeddings cache, gpt-4o-mini default, cost ledger + alerts | 20
2 | Copyright complaints on uploaded books | Legal | 3 | 4 | Curate from public-domain + Ministry curriculum; teacher attestation; DMCA-style takedown process | 12
3 | Click/Payme integration delays | Ops | 3 | 4 | Start integration in W8; manual bank transfer + admin grant as fallback | 12
4 | iOS App Store rejection | Ops | 2 | 3 | Submit early, clear content policy; ed-tech well-received | 6
5 | Scanned-book OCR misses context | Tech | 3 | 3 | OCR confidence threshold; admin re-process button; multi-language Tesseract training | 9
6 | Low user retention | Product | 3 | 5 | Streaks, daily challenge, push reminders, low premium price (29k UZS) | 15
7 | Founder burnout (solo) | People | 3 | 5 | 30h/week ceiling; design + content outsourced; hire content lead at month 4 | 15
8 | Telegram channel ban (key acq channel) | Marketing | 2 | 4 | Diversify channels; build email + push as owned audience | 8
9 | Supabase/Hetzner outage | Infra | 2 | 4 | Daily pg_dump to R2; documented restore runbook; UptimeRobot alerts | 8
10 | AI hallucinations in answers | Product | 4 | 4 | Mandatory citations; flag/feedback button; quality_score on questions; human review queue | 16
11 | Cheating in exams | Product | 4 | 3 | Server-authoritative timing, randomization, device fingerprint, tab-blur flags | 12
12 | Regulatory: edtech licensing in UZ | Legal | 2 | 4 | Engage local counsel; register as IT-Park resident (tax + legal benefits) | 8
13 | Currency devaluation (UZS) | Finance | 3 | 3 | Price in UZS but pay USD costs; raise prices annually with inflation | 9
14 | Talent acquisition (Kotlin/Flutter in UZ) | People | 3 | 4 | Hire remote from Tashkent IT-Park; partner with TUIT for interns | 12
15 | Competitor with deeper pockets enters | Market | 3 | 4 | Move fast, lock in school+center distribution, build moat via DTM question bank | 12

## KPI Dashboard
North-Star KPIs
# | Metric | Definition | MVP target (W14) | Year-1 target (M12)
1 | WAU | Weekly active users | 500 | 50,000
2 | DAU/MAU | Stickiness | 20% | 35%
3 | Questions answered / user / week | Engagement | 50 | 120
4 | Books opened / user / month | Engagement | 1 | 3
5 | AI chat messages / user / week | AI engagement | 5 | 30
6 | Conversion free → Premium | Monetization | 1.5% | 4%
7 | Churn (monthly) | Retention | — | <7%
8 | MRR (USD) | Monthly recurring revenue | — | $15,000
9 | ARPU (paying) | Average revenue per paying user | — | $3.50
10 | AI cost / paying user / month | Margin sanity | <$2.00 | <$1.50
11 | Gross margin | (MRR − COGS) / MRR | — | >45%
12 | Crash-free sessions (mobile) | Quality | >99% | >99.5%
13 | API p95 latency (non-AI) | Quality | <500ms | <400ms
14 | Uptime (rolling 30d) | Quality | 99.5% | 99.9%
15 | Net Promoter Score (NPS) | Sentiment | 30 | 50
16 | Books indexed and AI-ready | Content depth | 50 | 5,000
17 | Teacher accounts | B2B / community | 5 | 1,000
18 | Learning centers | B2B | 0 | 20